April 2026 monitoring

Organisation: Ashfield District Council

Capacity funding activities

| Delivered activity details | There are 8 answers Answers for “Delivered activity details” |
| --- | --- |
| Do you have any capacity funding left to spend? | Yes |
| Planned activity details | There is 1 answer Answers for “Planned activity details” |
| Have you delivered any projects using programme delivery funding? | No |

Delivered activity details

Consultancy Support

| What is the name of the activity or group of activities? | Consultancy Support |
| --- | --- |
| Which category does Consultancy Support most relate to? | Consultancy |
| Tell us more about this consultancy related activity | Support to define the initial LTPFT vision, objectives and priorities. Facilitated the LTPFT process (data and engagement analysis, strategic planning, identification of interventions etc.) Developed LTPFT 10-year strategy and 3-year investment plan. London based firm awarded. (Due to value went through relevant procurement process) |
| How much Pride in Place funding did you spend on Consultancy Support? | £33,575 |

Consultancy Support

| What is the name of the activity or group of activities? | Consultancy Support |
| --- | --- |
| Which category does Consultancy Support most relate to? | Community outreach and engagement |
| Tell us more about this consultancy related activity | School outreach and engagement support - 35 young people took part in a range of activities to share their views. They looked at the areas of the investment, and they shared thoughts. A written report was produced. Direct Award due to value and Nottingham based company. Julia Hayes is an experienced consultant in inclusion and participation, with a background as an Educational Psychologist, graphic facilitator and teacher. She is passionate about finding creative ways to include marginalised children and adults in their local services and community. |
| How much Pride in Place funding did you spend on Consultancy Support? | £1,353 |

Consultancy Support

| What is the name of the activity or group of activities? | Consultancy Support |
| --- | --- |
| Which category does Consultancy Support most relate to? | Community outreach and engagement |
| Tell us more about this consultancy related activity | Development of community engagement survey which was made publicly available and provision of analytical support for survey results including written report and feedback. A total of 344 people completed the first phase of the consultation. |
| How much Pride in Place funding did you spend on Consultancy Support? | £6,250 |

ADC Staff time 24/25

| What is the name of the activity or group of activities? | ADC Staff time 24/25 |
| --- | --- |
| Which category does ADC Staff time 24/25 most relate to? | Management costs |
| Tell us more about this management cost related activity | Admin support - board administration |
| How much Pride in Place funding did you spend on ADC Staff time 24/25? | £3,571 |

Engagement Support

| What is the name of the activity or group of activities? | Engagement Support |
| --- | --- |
| Which category does Engagement Support most relate to? | Community outreach and engagement |
| Tell us more about this community outreach activity | The owner of a high street business, Showstoppers visited every shop in the town (approx 87 businesses), providing information and a poster to display about the surveys to encourage business and resident participation. |
| How much Pride in Place funding did you spend on Engagement Support? | £500 |

ADC staff time 25/26

| What is the name of the activity or group of activities? | ADC staff time 25/26 |
| --- | --- |
| Which category does ADC staff time 25/26 most relate to? | Management costs |
| Tell us more about this management cost related activity | Admin support - board administration |
| How much Pride in Place funding did you spend on ADC staff time 25/26? | £24,000 |

Engagement Support

| What is the name of the activity or group of activities? | Engagement Support |
| --- | --- |
| Which category does Engagement Support most relate to? | Community outreach and engagement |
| Tell us more about this community outreach activity | Ashfield Voluntary Action (AVA) the infrastructure lead organisation for the area allocated 25 days of officer time to promote the consultation through going out to groups, taking leaflets and putting up notices; talking to groups through phone calls and emails, explaining the process and providing a weekly information desk in the health hub. They supported people who are not IT literate to complete a written response. AVA allocated 4 days of marketing work emailing all contacts and promoting on their website and Facebook pages. Our Centre which provides community transport and activities for older people spoke to people and supported them to fill out surveys, they ran 3 face to face sessions for Stage 1 and 2 face to face sessions for stage 2. These completed surveys were added to our overall total number of surveys recieved throughout our two consultations. |
| How much Pride in Place funding did you spend on Engagement Support? | £2,750 |

Promotional activity and materials

| What is the name of the activity or group of activities? | Promotional activity and materials |
| --- | --- |
| Which category does Promotional activity and materials most relate to? | Community outreach and engagement |
| Tell us more about this community outreach activity | Promotional materials and activity to support public consultation/survey work. |
| How much Pride in Place funding did you spend on Promotional activity and materials? | £928 |

Planned activity details

Quick Win project

| What is the name of the activity or group of activities? | Quick Win project |
| --- | --- |
| Which category does Quick Win project most relate to? | Other |
| Describe this planned activity | Funding to Abbey Hill Primary school with removal of asbestos from part of their premises to support the creation of a dedicated community space. |
| What is the estimated cost of this activity? | £10,000 |

Projects delivered using programme funding

| Planned projects | There are 3 answers Answers for “Planned projects” |
| --- | --- |

Planned projects

Digital Inclusion

| What is the name of the planned project? | Digital Inclusion |
| --- | --- |
| Tell us more about Digital Inclusion | Every student starting Year 10 in September 2026 will be given a Chromebook as part of a two-year pilot at Outwood Academy to support them through Years 10 and 11, as well as into further education and employment. This is an investment into the students themselves, rather than the school, opening digital opportunities for young people that need it the most. |
| Who does it target? | Children and young people |
| Does Digital Inclusion relate to a physical asset? | No |
| Which intervention does Digital Inclusion relate to the most? | Regeneration, high streets and heritage |
| Which other intervention does Digital Inclusion relate to? | Education and opportunity |
| Which organisations are going to deliver Digital Inclusion? | Public sector |
| What are the names of these organisations? | Outwood Academy Kirkby in Ashfield |
| What will the total capital spend be for Digital Inclusion? | £78,451 |
| How much of the total capital spend will be paid using Pride in Place Programme capital funding? | £78,451 |
| What will the total revenue spend be for Digital Inclusion? | £0 |
| How much of the total revenue spend will be paid using Pride in Place Programme revenue funding? | £0 |
| Start date for Digital Inclusion | 1 April 2026 |
| Planned end date for Digital Inclusion | 1 August 2028 |
| Will you be using programme delivery funding for any management costs? | Yes |
| Tell us about the planned management costs you will spend programme funding on | Project Management and administration. The total will be decided at the end of the financial year through completion of a timesheet as agreed by board so £0 will be entered at this stage. The maximum claim across the whole programme is 4%. |
| How much programme delivery funding will you spend on management costs? | £0 |

Morvern Park Play zone

| What is the name of the planned project? | Morvern Park Playzone |
| --- | --- |
| Tell us more about Morvern Park Playzone | Creating a safe, accessible, all-weather multi-use games area to support increased activity levels, health inequalities and limited youth provision |
| Who does it target? | Children and young people Disabled residents Ethnic minority communities Older residents Whole community |
| Does Morvern Park Playzone relate to a physical asset? | Yes |
| Tell us the postcode where the project will be delivered | NG17 7BX |
| Which intervention Does Morvern Park Playzone relate to the most? | Regeneration, high streets and heritage |
| Which other intervention does Morvern Park Playzone relate to? | Health and wellbeing |
| Which organisations are going to deliver Morvern Park Playzone? | Local authority |
| What are the names of these organisations? | Ashfield District Council |
| What will the total capital spend be for Morvern Park Playzone? | £349,908 |
| How much of the total capital spend will be paid using Pride in Place Programme capital funding? | £99,909 |
| What will the total revenue spend be for Morvern Park Playzone? | £0 |
| How much of the total revenue spend will be paid using Pride in Place Programme revenue funding? | £0 |
| Start date for Morvern Park Playzone | 1 March 2026 |
| Planned end date for Morvern Park Playzone | 1 February 2027 |
| Will you be using programme delivery funding for any management costs? | Yes |
| Tell us about the planned management costs you will spend programme funding on | Project Management and administration. The total will be decided at the end of the financial year through completion of a timesheet as agreed by board so £0 will be entered at this stage. The maximum claim across the whole programme is 4%. |
| How much programme delivery funding will you spend on management costs? | £0 |

Titchfield Park

| What is the name of the planned project? | Titchfield Park |
| --- | --- |
| Tell us more about Titchfield Park | Provide a new pavilion for the bowls, football and netball clubs which regularly use the site, upgrading the existing netball courts with new surfacing and energy efficient floodlights and general improvements which include resurfacing of footpaths. |
| Who does it target? | Children and young people Disabled residents Ethnic minority communities Older residents Whole community |
| Does Morvern Park Playzone relate to a physical asset? | Yes |
| Tell us the postcode where the project will be delivered | NG17 8DT |
| Which intervention Does Morvern Park Playzone relate to the most? | Regeneration, high streets and heritage |
| Which other intervention does Morvern Park Playzone relate to? | Health and wellbeing |
| Which organisations are going to deliver Morvern Park Playzone? | Local authority |
| What are the names of these organisations? | Ashfield District Council |
| What will the total capital spend be for Morvern Park Playzone? | £601,315 |
| How much of the total capital spend will be paid using Pride in Place Programme capital funding? | £591,588 |
| What will the total revenue spend be for Morvern Park Playzone? | £0 |
| How much of the total revenue spend will be paid using Pride in Place Programme revenue funding? | £0 |
| Start date for Morvern Park Playzone | 1 March 2026 |
| Planned end date for Morvern Park Playzone | 1 February 2028 |
| Will you be using programme delivery funding for any management costs? | Yes |
| Tell us about the planned management costs you will spend programme funding on | Project Management and administration. The total will be decided at the end of the financial year through completion of a timesheet as agreed by board so £0 will be entered at this stage. The maximum claim across the whole programme is 4%. |
| How much programme delivery funding will you spend on management costs? | £0 |

Neighbourhood board details

| Have any of your neighbourhood board members left in the last 6 months? | Yes |
| --- | --- |
| Have any new members joined your neighbourhood board in the last 6 months? | Yes |
| Neighbourhood board members who have left | There are 2 answers |
| Neighbourhood board members who have joined | There is 1 answer |

Neighbourhood board members who have left

Mark Scattergood-Cawar

| Name of the member who has left | Mark Scattergood-Cawar |
| --- | --- |
| Occupation of the member | Local Business owner |
| Tell us why the member left the board | Left due to other commitments |

Joelle Davies

| Name of the member who has left | Joelle Davies |
| --- | --- |
| Occupation of the member | Nottinghamshire County Council Employee |
| Tell us why the member left the board | Left county council - awaiting confirmation of replacement |

Neighbourhood board members who have joined

Sarah Kirk

| Name of the member who has left | Sarah Kirk |
| --- | --- |
| Occupation of the member | Health Activity and Wellbeing Manager - Ashfield Contract, Everyone Active |
| Tell us why the member left the board | Replacement for previous representative |

Forecast capacity funding spend

| Which types of activities do you expect to spend Pride in Place capacity funding on over the next financial year? | Community outreach and engagement Training Other |
| --- | --- |
| What is the estimated total forecast capital spend for community related activities? | £0 |
| What is the estimated total forecast revenue spend for community related activities? | £16,000 |
| What is the estimated total forecast spend for training related activities? | £1,000 |
| What is the estimated total forecast capital spend for any other activities? | £0 |
| What is the estimated total forecast revenue spend for any other activities? | £109,531 |

Forecast programme delivery funding spend

| Which interventions do you expect to spend Pride in Place programme delivery funding on over the next financial year? | Cohesion Education and opportunity Regeneration, high streets and heritage Safety and security Work, productivity and skills |
| --- | --- |
| What is the estimated total forecast capital spend on cohesion? | £0 |
| What is the estimated total forecast revenue spend on cohesion? | £62,000 |
| What is the estimated total forecast capital spend on education and opportunity? | £0 |
| What is the estimated total forecast revenue spend on education and opportunity? | £45,000 |
| What is the estimated total forecast capital spend on regeneration, high streets and heritage? | £360,000 |
| What is the estimated total forecast revenue spend on regeneration, high streets and heritage? | £0 |
| What is the estimated total forecast capital spend on safety and security? | £0 |
| What is the estimated total forecast revenue spend on safety and security? | £15,000 |
| What is the estimated total forecast capital spend on work, productivity and skills? | £0 |
| What is the estimated total forecast revenue spend on work, productivity and skills? | £30,000 |
| How much do you expect to spend on management costs related to project delivery? | £23,680 |

Outputs

| Select all the outputs that are relevant to what you've done in your neighbourhood | None of these outputs are relevant to my projects |
| --- | --- |