## Hucknall concise
ANTICIPATED ANNUAL DELIVERY OF SITES AS INCLUDED IN THE UPDATED OCTOBER 2025 TRAJECTORY [ADC.20]. PURPLE TEXT REPRESENTS POSITION AT 3rd DECEMBER 2025
ALP 2023-2040 Ref | Planning Appn Ref | Database/ SHELAA/ Brownfield Register Site Ref | Address | Site Area | Total number of Dwellings on site | Total number of Dwellings remaining at 1st April 2025 | Status at 1st December 2025 | 23/24 Actual Delivery | 24/25 Actual Delivery | Year 1 25/26 | Year 2 26/27 | Year 3 27/28 | Year 4 28/29 | Year 5 29/30 | Year 6 30/31 | Year 7 31/32 | Year 8 32/33 | Year 9 33/34 | Year 10 34/35 | Year 11 35/36 | Year 12 36/37 | Year 13 37/38 | Year 14 38/39 | Year 15 39/40 | Total remaining 2025 - 2040 | Developer/ promoter | Summary Notes | new LP settlement hierarchy
Proposed H1 allocations without Planning Permission
H1Ha | n/a | HK009 | Seven Stars Public House and adjoining land, West Street | 0.7 | 28 | 28 | No permission | [8 empty] | 28 | [8 empty] | 28 | None currently known | Vacant brownfield site in Main Urban Area. Some developer interest but no current proposal. | MUA
H1Hb | V/2020/0855 V/2024/0103 | HK013 | Linby Boarding Kennels, East of Church Lane, Hucknall | 1.6 | 43 | 34 | No permission for majority of site. Full permission on northern part. | [9 empty] | 34 | [7 empty] | 34 | Swan Homes (part) | Planning permission for 9 dwellings on northern brownfield part of site (V/2024/0103). Yield reduced from 43 to avoid double counting. | MUA
H1Hc | V/2025/0405 (part of site only) | HK051 | Land north of A611 / South of Broomhilll Farm, Hucknall | 31 | 5 | 499 | Pending decision - Part of site only | [7 empty] | 9 | 70 | 70 | 70 | 70 | 70 | 70 | 70 |  |  | 499 | Bellway Homes (part) | Full appplication submitted July 2025 for 84 dwgs on allotments part of site SHELAA ref. HK043 (V/2025/0405). (composite site - HK016, HK034, HK043,HK050). Majority owned by NCC. HS10.14a (DLP obo Bellway Homes) - support for site allocation & outlines how landowners/promoters/developers are working collaboratively to ensure comprehansive development. Positive engagement with Council and Highways to progress application for 84 units. | MUA
H1Hd | n/a | HK022 | Land adjoining Stubbing Wood Farm, Watnall Road, Hucknall | 8.82 | 198 | 198 | No permission | [10 empty] | 35 | 35 | 35 | 35 | 35 | 23 |  | 198 | None currently known | SHELAA site HK022 deemed devalopable. The Council have prepared a Masterplan for the site which addresses key issues and requirements, including the approach to important heritage aspects. | MUA
| Total Hucknall H1 sites without planning permission |  |  |  |  | 759 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 98 | 104 | 105 | 105 | 105 | 105 | 105 | 23 | 0 | 759 |  |  | MUA
| Proposed H1 alllocations with Full/Reserved Matters/Detailed Planning Permission | [26 empty] | MUA
H1Hn | V/2019/0483 | H0335 | Phase 2, Broomhill Farm, Nottingham Road | 7.16 | 217 | 62 | Full/RM permission | 71 | 35 | 35 | 27 | [13 empty] | 62 | Bellway Homes | Site Under Construction | MUA
H1Hl | V/2020/0563 | H0265 | Land at, Shepherd Street, Rolls Royce | 1.34 | 100 | 0 | Full/RM permission | 48 | [17 empty] | Persimmon Homes | Site complete 4/24.
H1He | V/2022/0652 | H0265h | Phase 5b, Former Rolls Royce Site, Off Watnall Road | 3.84 | 150 | 83 | Full/RM permission | 0 | 67 | 43 | 40 | [13 empty] | 83 | Persimmon Homes | Site Under Construction | MUA
H1Hf | V/2022/0644 | H0265i | Phase 9, Former Rolls Royce Site, Off Watnall Road | 4.12 | 101 | 78 | Full/RM permission | 0 | 23 | 40 | 38 | [13 empty] | 78 | Harron Homes | Site Under Construction | MUA
H1Hg | V/2022/0816 | H0239 | Hucknall Town Football Club, Watnall Road | 2.52 | 83 | 67 | Full/RM permission | 0 | 16 | 35 | 32 | [13 empty] | 67 | Metropolitan Housing | Site Under Construction. V/2024/0551 increases yield to 83 from 81. To be brought forward as 100% affordable units | MUA
H1Ca | V/2021/0849 | H0371 | Former Hucknall Police Station, Watnall Road | 0.57 | 73 | 73 | Full/RM permission | 0 | 0 | 73 | [14 empty] | 73 | Preferred Homes LTD. | Site Under Construction. previously counted as a 73-bed care home as the original planning application referred to C2 class. However, the approved development is for the erection of 73 self-contained 1 and 2 bed apartments for designed as a retirement solution for residents who can live independently but need some elements of support. The commitment is now counted more accurately as individual apartments rather than a C2 care home. The apartments are expected to be completed by Spring 2026. | MUA
| Total Hucknall Large Sites with Detailed Permission |  |  |  |  | 363 |  | 119 | 141 | 226 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363 |  |  | MUA

## Kirkby concise
ANTICIPATED ANNUAL DELIVERY OF SITES AS INCLUDED IN THE UPDATED OCTOBER 2025 TRAJECTORY [ADC.20]. PURPLE TEXT REPRESENTS POSITION AT 3rd DECEMBER 2025
ALP 2023-2040 ref | Planning Appn Ref | Database/ SHELAA/ Brownfield Register Site Ref | Address | Site Area | Total number of Dwellings on site | Total number of Dwellings remaining at 1st April 2025 | Status at 1st December 2025 | 23/24 Actual Delivery | 24/25 Actual Delivery | Year 1 25/26 | Year 2 26/27 | Year 3 27/28 | Year 4 28/29 | Year 5 29/30 | Year 6 30/31 | Year 7 31/32 | Year 8 32/33 | Year 9 33/34 | Year 10 34/35 | Year 11 35/36 | Year 12 36/37 | Year 13 37/38 | Year 14 38/39 | Year 15 39/40 | Total remaining 2025 - 2040 | Developer/ promoter | Summary Notes | new LP settlement hierarchy
Proposed H1 allocations without Planning Permission
H1Ka | n/a | KA002 | Beacon Farm, Derby Road, Kirkby-In Ashfield | 1.5 | 41 | 41 | No permission | [9 empty] | 35 | 6 | [6 empty] | 41 | None currently known | Developer interest likely post allocation (advised by agent). HS10.2.1 (John Collins) in support of site alllocation. | MUA - Kirkby
H1Kc | n/a | KA011 | Land at Doles Lane, Kirkby-In Ashfield | 2.39 | 54 | 54 | No permission | [10 empty] | 19 | 35 | [5 empty] | 54 | Peveril Homes | Brownfield site. Land available within 5 years. Pre- application advice sought on a larger site which encompasses this area (December 2024) HS.10.5 (Stone Planning obo Peveril Homes) - heritage statement , highways assessment/access plan and illustrative layout submitted for an extended site to accomodate 97 dwellings. Agent/developer proposes delivery within 5 years. | MUA - Kirkby
H1Ke | V/2010/0552 - lapsed | KA026 | former allotments land at Diamond Ave | 2.2 | 63 | 63 | Pending decision | [7 empty] | 35 | 28 | [8 empty] | 63 | Homes by Honey | Currently in ADC ownership. Options for an appropriate development are being explored. Full planning application for 63 dwellings pending decision (V/2024/0637). | MUA - Kirkby
H1Kg | n/a | KA038 | Rear 126 Skegby Road, Annesley | 0.55 | 15 | 15 | No permission | [7 empty] | 15 | [9 empty] | 15 | None currently known | Located in Main Urban Area and land is available within 5 years, however does not meet NPPF deliverable definition. | MUA - Kirkby
H1Kh | n/a | KA046 | Hucknall Road, Newstead | 1.55 | 47 | 47 | No permission | [12 empty] | 35 | 12 |  |  |  | 47 | None currently known | Green Belt site. Land available within 5 years but doesn’t meet NPPF deliverable definition. | NS - Annesley/Newstead
H1Km | V/2023/0312 - resolution to grant O/L pp subject to signing a s106 agreement | KA024 | Abbey Road, Kirkby | 1.57 | 38 | 38 | Resolution to grant O/L subject to signing a s106 agreement | [7 empty] | 3 | 35 | [8 empty] | 38 | None currently known | Resolution to grant O/L pp subject to signing s106. Letter from SoS MHCLG 14/03/2025 stating no call in necessary re. green belt. A draft s106 agreement is in place. Signed s106 received from third party - diarised for ADC signing on Tuesday 9th December 2025. | MUA - Kirkby
H1Kn | V/2018/0333 - lapsed | KA057 BRF12 | Southwell Lane, Kirkby | 1.9 | 60 | 60 | No permission | [6 empty] | 30 | 30 | [9 empty] | 60 | Welbeck Estates | Vacant Brownfield Site within Main Urban Area. Cabinet 9th June 2025 approved the proposal for ADC to purchase and develop as part of its Affordable Housing Development Programme. Pre-application advice has been sought - progress towards developing the site. | MUA - Kirkby
H1Kn | n/a – ADC housing programme | KA058 | former Kirklands care home, Fairhaven, Kirkby | 0.54 | 20 | 20 | Pending decision |  |  |  | 20 | [13 empty] | 20 | ADC | Vacant Brownfield Site within Main Urban Area. At a meeting on 16th September 2024 ADC Cabinet approved a proposal for ADC to purchase and develop the site as a continuation of its successful Affordable Housing Development Programme. A Full planning application for 20 dwellings (V/2025/0544) is currently being considered and illustrates clear progress towards development of the site. | MUA - Kirkby
H1Kp | n/a – Towns fund project | KA059 | Pond Hole, Kirkby | 0.4 | 54 | 54 | No permission |  |  |  | 19 | 35 | [12 empty] | 54 | ADC/ Langcroft Group | Brownfield site located in Kirkby Town centre. Forms part of the Towns Funds programme with a grant secured for remediation work for North Kirkby Gateway Project including 55 retirement homes - anticipated delivery in 2-3 years as publicised. | MUA - Kirkby
H1Kq | V/2024/0422 V/2025/0433 | KA060 | Former Wyvern Club site, Lane End, Kirkby | 0.4 | 12 | 12 | Full PP for demolition. Decision pending for development |  |  |  | 12 | [13 empty] | 12 | ADC | Vacant brownfield site located on the edge of Kirkby Town centre. Ashfield District Council have now secured the land, purchased through Towns Fund investment. The vacant building has been demolished (October 2025), site cleared and a planning application has been submitted for the construction of 12 apartments (V/2025/0433). Recommended for approval going to Plannning Committee 12th December 2025. | MUA - Kirkby
H1Kr | V/2025/0676 Towns fund project | KA061 | Ellis Street, Kirkby | 0.05 | 24 | 24 | Pending decision |  |  |  | 24 | [13 empty] | 24 | ADC | Brownfield site located in Kirkby Town centre. Ashfield District Council have now secured the land, purchased through Towns Fund investment, and pre-application advice has been sought for the proposed development for mixed residential/commercial use. Factory shop now demolished. Full applicationfor mixed use development with 20 apartments now pending at 2nd December 2025. | MUA - Kirkby
| Total Kirkby sites without planning permission |  |  |  |  | 428 |  | 0 | 0 | 0 | 75 | 35 | 0 | 30 | 83 | 63 | 35 | 25 | 35 | 35 | 12 | 0 | 0 | 0 | 428
| Proposed H1 alllocations with Full/Reserved Matters/Detailed Planning Permission | [26 empty] | MUA
H1Kf | V/2022/0326 | K0306 | Warwick Close, Kirkby | 0.83 | 34 | 0 | Full/RM permission | 34 | [16 empty] | 0 | ADC | Site Complete 4/24 | MUA - Kirkby
H1Kb | V/2019/0756 | K0283 | Land off Millers Way, NG17 8RF | 1.4 | 54 | 0 | Full/RM permission | 15 | 39 | [15 empty] | 0 | Peveril Homes | Site complete 4/25 | MUA - Kirkby
H1Kd | V/2020/0518 | K0322 | Coxmoor lodge farm, Farm View Road/Walesby drive | 7.31 | 196 | 196 | Full/RM permission |  |  | 35 | 35 | 35 | 35 | 35 | 21 | [9 empty] | 196 | Gleesons | Site under construction 4/25. Addresses named and numbered - delivery current year. Holinwell heath website indicates 39 dwellings sold/reserved/for sale at October 2025. | MUA - Kirkby
H1Kl | V/2024/0060 | K0329 | Land Off Central Avenue Kirkby in Ashfield | 0.47 | 16 | 16 | Full/RM permission |  |  | 16 | [14 empty] | 16 | ADC | ADC affordable homes scheme - nearing completion October 2025. | MUA - Kirkby
H1Kk | V/2020/0627 | K0219 | Land off Laburnum Ave | 1.11 | 38 | 38 | Full/RM permission |  |  |  |  | 20 | 18 | [11 empty] | 38 | East Midlands Housing | 100% affordable housing. Groundworks underway at April 2025 and several conditions discharged July 2025 indicating clear progress. Likely to be delivered earlier than anticipated. | MUA - Kirkby
| Total Kirkby Large Sites with Detailed Permission |  |  |  |  | 250 |  | 49 | 39 | 51 | 35 | 55 | 53 | 35 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250

## Sutton concise
ANTICIPATED ANNUAL DELIVERY OF SITES AS INCLUDED IN THE UPDATED OCTOBER 2025 TRAJECTORY [ADC.20]. PURPLE TEXT REPRESENTS POSITION AT 3rd DECEMBER 2025
ALP 2023-2040 ref | Planning application Ref | Database/ SHELAA/ Brownfield Register Site Ref | Address | Site Area | Total number of Dwellings on site | Total number of Dwellings remaining at 1st April 2025 | Status at 1st December 2025 | 23/24 Actual Delivery | 24/25 Actual Delivery | Year 1 25/26 | Year 2 26/27 | Year 3 27/28 | Year 4 28/29 | Year 5 29/30 | Year 6 30/31 | Year 7 31/32 | Year 8 32/33 | Year 9 33/34 | Year 10 34/35 | Year 11 35/36 | Year 12 36/37 | Year 13 37/38 | Year 14 38/39 | Year 15 39/40 | Total remaining 2025 - 2040 | Developer/ promoter | Summary Notes | new LP settlement hierarchy
Proposed H1 allocations without Planning Permission
H1Sb | V/2021/0792 | SA009 | South of Vision West Nottinghamshire College, Cauldwell Road, Sutton-In-Ashfield | 9.24 | 208 | 208 | Resolution to grant O/L pp subject to signing a s106 agreement | [7 empty] | 35 | 35 | 35 | 35 | 35 | 33 |  |  |  |  | 208 | None currently known | Nottinghamshire County Council owned. Total site area of 10.4 Ha with small part in Mansfield District. Included for 208 only in Ashfield part. Resolution to grant O/L pp subject to S106 (V/2021/0792). A draft s106 agreement has been prepared. | Mansfield
H1Sd | V/2023/0275 | SA016 & SA044 | Adj Oakham Business Park, Sutton-In-Ashfield | 9.99 | 250 | 250 | Resolution to grant O/L pp subject to signing a s106 agreement | [6 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 5 |  |  |  | 250 | None currently known | Part ADC owned. Resolution to grant O/L permission for 250 dwellings subject to signing a s106 (planning committee11/06/25). A draft s106 and s111 agreement is currently being worked up. | Mansfield
H1Se | V/2022/0133 | SA017 BFR8 | Land at Priestic Road/Northern View | 0.5 | 19 | 19 | No permission | [10 empty] | 19 | [6 empty] | 19 | None currently known | Brownfield site within the Main Urban Area (BFR 8). V/2022//0133 for 19 dwellings - no decision made. Pre application advice has since been sought for 22 dwellings on this site (October 2024) | MUA - Sutton
H1Sf | V/2024/0587 | SA022 | Rear 23 Beck Lane, Skegby | 0.84 | 33 | 33 | Full/RM permission |  |  |  |  | 33 | [12 empty] | 33 | Griffiths Services and Developments | A full planning application for 33 homes is currently being considered on this site (V/2024/0587) . A draft s106 agreement has been prepared illustrating clear progress towards developing the site. s106 agreement signed and decision issued 1st December 2025. The site will be brough forward for 100% affordable homes. | MUA - Sutton
H1Sh | n/a | SA025 | Pasture Farm, Alfreton Road, Sutton | 1.26 | 34 | 34 | No permission | [8 empty] | 34 | [8 empty] | 34 | Land promoter | Land available within 5 years but doesn’t meet NPPF deliverable definition. Developer has option to buy. HS10.8 (Inovo) sets out that: the site is under control of an experienced land promoter; title and access issues are resovled; Ground conditions have been evaluated and present no significant risk; Estimate a yield of 60 dwellings which could be delivered 2028-2030 | MUA - Sutton
H1Si | n/a | SA033 | Rear Kingsmill Hospital, Sutton-In-Ashfield | 14.64 | 264 | 264 | No permission | [9 empty] | 19 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 264 | None currently known | NCC owned. Deemed developable in SHELAA | MUA - Sutton
H1Sj | n/a | SA041 | Clegg Hill Drive, Huthwaite | 4.62 | 104 | 104 | No permission | [9 empty] | 34 | 35 | 35 | [5 empty] | 104 | None currently known | ADC owned. Deemed developable in SHELAA | MUA - Sutton
H1Sk | n/a | SA057 | Sunnyside Farm, Blackwell Road, Huthwaite | 18.89 | 350 | 350 | No permission | [7 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 350 | Persimmon | Developer interest. Pre application advice sought for construction of Approximately 350 Dwellings with Associated Access, Landscaping and Public Open Space. Estimated yield based on sketch plan submitted as part of LP Reg 19 consultation. HS10.17.1 (Marrons obo Persimmon) details a Phase 1 site investigation report and geopysical surveys which conclude that made ground affects only 2% of the site and that the natural ground is a suitably solid base for traditional foundations; contaminated land and historic mine activity is relatively normal for the area and can be accomommdated within the layout without predjucing delivery of the site. | MUA - Sutton
H1Sn | n/a | SA064 | Adj Molyneux Farm, Fackley Road, Teversal | 0.5 | 14 | 14 | No permission | [11 empty] | 14 | [5 empty] | 14 | None currently known | no known activity | Fackley
H1So | n/a | SA065 | off Fackley Road, Teversal | 0.44 | 12 | 12 | No permission | [11 empty] | 12 | [5 empty] | 12 | None currently known | no known activity | Fackley
H1Sr | V/2023/0417 | S0665 SA071 | Land at, Clare Road | 2.92 | 69 | 69 | Full/RM permission |  |  |  | 35 | 34 | [12 empty] | 69 | East Midlands Housing | lapsed - granted 18/08/2021. Permission granted under ref V/2020/0791. An amended scheme for 100% affordable housing is currently being assessed (V/2023/0417). A s106 agreement is currently being finalised for the amended scheme. s106 agreement signed and decision issued 21st November 2025. | MUA - Sutton
H1Ss | V/2023/0679 | SA074 | Land to the east off A6075 Beck Lane, Skegby | 11.8 | 230 | 230 | Resolution to grant O/L subject to signing a s106 agreement | [6 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 20 |  |  |  |  | 230 | Richborough Estates Group Ltd | Resolution to grant O/L permission subject to signing a s106 (planning committee 11/06/25). A draft s106 agreement is currently being finalised | MUA - Sutton
H1St (majority of site) | V/2022/0054 (small part of site only) | SA082 | Blackwell Road/ Main Street, Huthwaite | 4.42 | 90 | 90 | Small part permitted for 9 dwellings. No permission on remainder | [7 empty] | 35 | 35 | 20 | [7 empty] | 90 | Evolution Homes | Developer interest. 9 dwellings on southern part of site granted permission 3/6/24 (V/2022/0601) and has subsequently had some conditions discharged (V/2024/0486) . Yield on this remaining part reduced to 90 dwellings to account for small site permission of 9 dwellings. HS10.16 (Stainton planning) promoting site obo Evolution Homes who currently have options agreements on approx.70% of site (phases 1-4) which they estimate will deliver 66 dwellings within 5 years. Phase 5 (to the north) is currently under negotiation with the landowner. | MUA - Sutton
H1Su | V/2023/0054 (small part of site only) | SA084 | Rear 113 to 139 Beck Lane | 4.46 | 100 | 91 | Small part permitted for 9 dwellings. No permission on remainder | [9 empty] | 35 | 35 | 21 | [5 empty] | 91 | Homes by Honey | PP for 9 dwellings granted Feb 2024 (V/2023/0054). Site yield reduced from 100 to 91 accordingly to avoid double counting with small site data. HS10.14a (DLP obo Kieth Haslam) Homes by Honey in dialogue with landowner; No significant physical constraints and Floodzone 1; deemed suitable for up to 134 dwellings | MUA - Sutton
H1Sz | V/2020/0411 - Lapsed | S0293 BFR22 | land at Outram Street/Park Street | 0.23 | 24 | 24 | No permission | [7 empty] | 24 | [9 empty] | 24 | None currently known | Brownfield site on edge of town centre within Main Urban Area. Reserved matters permission for RM for 24 apartments now lapsed | MUA - Sutton
H1Sad | V/2022/0878 - Pending | S0638 BFR36 | The Pattern House, Crossley Avenue, Huthwaite, | 0.68 | 23 | 23 | Pending decision | [7 empty] | 23 | [9 empty] | 23 | Munkbridge Homes | Outline permission for 23 dwellings V/2018/0212 now lapsed. Full PP pending V/2022/0878 dwellings. | MUA - Sutton
H1Sah | V/2022/0347 - Pending | BFR40 | Land adjacent no.208 Mansfield Road, Sutton in Ashfield | 0.96 | 36 | 36 | Pending decision | [5 empty] | 10 | 26 | [10 empty] | 36 | Peveril Homes | Peveril Homes application V/2022/0347 for 36 dwellings pending. Previous permission for housing established principle. Currently refining highways aspects. | MUA - Sutton
H1Sam | n/a | SA008 | Beck Lane South, Skegby |  | 106 | 106 | No permission | [10 empty] | 36 | 35 | 35 |  |  |  |  | 106 | None currently known | NCC owned. County Council is in detailed discussions with a third party regarding the provision of a suitable access to the site. It is envisaged that the land will be available in the medium term. Pre-application advice has been sought on this site. NCC now have a colboration agreement in place in respect of access from Omberley Avenue (included within PP for site H1Sf). | MUA - Sutton
H1San | V/2024/0489 | S0745 | Radford's farm, Dawgates Lane, Skegby | 4.5 | 90 | 90 | Resolution to grant O/L subject to signing a s106 agreement | [12 empty] | 20 | 35 | 35 |  |  | 90 | None currently known | Resolved to grant Outline planning permission for up to 90 dwellings subject to signing a s106 – Planning Committee 5th Feb 2025 (V/2024/0489) | Outer area - north Sutton
| Total Sutton sites without planning permission |  |  |  |  | 2047 |  | 0 | 0 | 0 | 35 | 67 | 10 | 96 | 222 | 209 | 248 | 300 | 292 | 213 | 110 | 105 | 70 | 70 | 2047
| Proposed H1 allocations with Outline Planning permission | [26 empty] | MUA
H1Sam | V/2022/0629 V/2025/0228 | S0744 | Land off Newark Road | 12.7 | 300 | 300 | Outline permssion | 0 | 0 | [5 empty] | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 20 |  | 300 | Harron Homes | Outline permission granted 11/02/25 (V/2022/0629) whole site 21.17Ha - applied standard assumption for net developable area (60%). V/2025/0228 Reserved Matters application for 300 dwellings pending 5/25. HS10.13a (pegasus obo Hallam Land) - Justified as fully aligns with Council's strategy. Aquired by Harron Homes and a reserved Matters application is currently being considered. | MUA - Sutton
H1Saj | V/2023/0613 |  | Land Between Redcliffe Street & Leyton Avenue, Sutton in Ashfield | 0.68 | 18 | 18 | Outline permssion | [7 empty] | 18 | [9 empty] | 18 | None currently known | Resolved to grant Outline permission subject to a s106 31st July 2024. Permission granted - s106 signed and decision notice issued 5th August 2025. | MUA - Sutton
| Total Sutton Large Sites with Outline Planning permission |  |  |  |  | 318 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 20 | 0 | 318
| Proposed H1 alllocations with Full/Reserved Matters/Detailed Planning Permission | [26 empty] | MUA
H1Saf | V/2021/0776 | S0454 | North of Midland Road | 0.48 | 20 | 0 | Full/RM permission | 20 | [16 empty] | 0 | ADC | Site complete 4/24 | MUA - Sutton
H1Sw | V/2018/0783 | S0498 | land off Gillcroft street/St Andrews Street & Vere Avenue, Skegby | 8.3 | 206 | 114 | Full/RM permission | 38 | 54 | 35 | 35 | 35 | 9 | [11 empty] | 114 | Gleesons | Site under construction | MUA - Sutton
H1Sy | V/2018/0120 | S0567 | off Brand Lane | 7.26 | 172 | 35 | Full/RM permission | 17 | 18 | 18 | 17 | [13 empty] | 35 | Harron Homes | Site under construction | MUA - Sutton
H1Sx | V/2016/0487 | S0575 | rear of 249-251 Alfreton Road, Sutton | 4.12 | 118 | 0 | Full/RM permission | 37 | 6 | [15 empty] | 0 | Gleesons | Site complete 4/25 | MUA - Sutton
H1Saa | V/2021/0089 | S0587 | Land at Beck Lane | 13.34 | 322 | 209 | Full/RM permission | 29 | 84 | 70 | 70 | 69 | [12 empty] | 209 | David Wilson/ Barret | Site under construction | MUA - Sutton
H1Sac | V/2020/0832 | S0638 | The Quarry, 57, Stoneyford Road, | 1.29 | 47 | 47 | Full/RM permission |  |  |  |  | 12 | 35 | [11 empty] | 47 | Linden Homes/ Metropolitan Housing Association | Site now under construction and likely to commence delivery Year 1. construction now underway and likely to deliver whole site earleir than previously anticipated. To be 100% affordable units. | MUA - Sutton
H1Sa | V/2020/0884 | S0658 | Land Rear of 211, Alfreton Road, NG17 1JP | 4.09 | 110 | 10 | Full/RM permission | 44 | 56 | 10 | [14 empty] | 10 | Countryside | Site nearing completion 4/25. | MUA - Sutton
H1Sae | V/2022/0262 | S0670 | Land Off, Ashland Road West | 10.46 | 300 | 300 | Full/RM permission | 0 | 0 | 70 | 70 | 70 | 70 | 20 | [10 empty] | 300 | Bellway | Site under construction 4/25 | MUA - Sutton
H1Sm | V/2021/0793 | SA061 | adjacent 88 High Hazels Drive, Huthwaite | 0.41 | 18 | 18 | Full/RM permission | 0 | 0 |  |  | 18 | [12 empty] | 18 | Unknown | s106 signed 15/05/2024 and decision notice issued. | MUA - Sutton
H1Sq | V/2024/0063 | S0740 | Hardwick Lane Rec | 1.08 | 40 | 40 | Full/RM permission | 0 | 0 | 40 | [14 empty] | 40 | ADC | ADC affordable homes programme - Under construction with anticipated completion of March 2026 | MUA - Sutton
H1Sl | V/2022/0295 | S0746 | North of Fackley Road, Teversal | 5.09 | 124 | 124 | Full/RM permission | 0 | 0 |  | 19 | 35 | 35 | 35 | [10 empty] | 124 | Persimmon | Full permission granted for 124 dwellings 3/1/25 (V/2022/0295). V/2025/0104 conditions 3,4,6,7 discharged 17/04/25 (V/2025/0104). Conditions 5, 8, 11 discharged 27/6/25 (V/2025/0296). Conditions 9, 10 ,15 discharged 30/07/25 (V/2025/0342). Illustrates clear progress towards development. Started on site | Fackley
H1Sai | V/2023/0156 | S0731 | Land at Pendean Way | 0.36 | 12 | 12 | Full/RM permission | 0 | 0 | 12 | [14 empty] | 12 | Global Developments LTD | Site under construction | MUA - Sutton
H1Sc | V/2020/0784 | S0675 | Land West Off, Fisher Close | 3.63 | 84 | 84 | Full/RM permission | 0 | 0 |  |  |  | 35 | 35 | 14 | [9 empty] | 84 | Avant | V/2024/0523 Reserved Matters permission granted 11/07/25. | MUA - Sutton
H1Sg | V/2023/0540 | SA023 | Former Miner's Welfare Sports Ground, Stanton Hill, Sutton-In-Ashfield | 3.75 | 112 | 112 | Full/RM permission | [5 empty] | 10 | 35 | 35 | 32 | [8 empty] | 112 | Gleesons | Resolution to grant PP subject to s106 at 5th Feb. 2025 Planning Committee. s106 signed and decision issued 19/06/2025. Street naming and numbering request received by ADC Nov.25 and developer estimates site completion date by Sept 2028. | MUA - Sutton
H1Sak | V/2022/0612 | SA026 (part) | Rookery Lane, Sutton | 2.74 | 78 | 78 | Full/RM permission |  |  |  | 8 | 35 | 35 | [11 empty] | 78 | Gleesons | Gleesons - being brought forward as a Phase 2 to the site under construction to the north. Forms eastern section of SHELAA site SA026. Resolution to approve subject to s106 (5th Feb 2025). s106 signed 30th June 2025. Conditions 4, 7, 8, 9, 11, 13, 14 discharged September 2025, indicating clear progress. | MUA - Sutton
H1Sag | V/2022/0109 | S0320 BFR14 | Quantum Clothing North St Huthwaite | 2.5 | 61 | 61 | Full/RM permission |  |  |  |  | 10 | 35 | 16 | [10 empty] | 61 | Gleesons | Vacant brownfield site in main Urban Area. Planning committee19th March 2025 resolution to grant permission - Reduced yield from 71 to 61 dwellings. S106 signed and decision issued 30/6/25 | MUA - Sutton
| Total Sutton Large Sites with Detailed Permission |  |  |  |  | 1244 |  | 185 | 218 | 255 | 219 | 284 | 264 | 141 | 49 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1244
NB In addition to the proposed housing allocations listed above, a new site for 104 homes has had a resolution to grant outline permission at 11th November 2025 Planning Committee (V/2024/0522). Site proposed for 100% affordable homes.

## Rurals concise
ANTICIPATED ANNUAL DELIVERY OF SITES AS INCLUDED IN THE UPDATED OCTOBER 2025 TRAJECTORY [ADC.20]. PURPLE TEXT REPRESENTS POSITION AT 3rd DECEMBER 2025
ALP 2023-2040 Ref | Planning application Ref | Database/ SHELAA/ Brownfield Register Site Ref | Address | Site Area | Total number of Dwellings on site | Total number of Dwellings remaining at 1st April 2025 | Status at 1st December 2025 | 23/24 Actual Delivery | 24/25 Actual Delivery | Year 1 25/26 | Year 2 26/27 | Year 3 27/28 | Year 4 28/29 | Year 5 29/30 | Year 6 30/31 | Year 7 31/32 | Year 8 32/33 | Year 9 33/34 | Year 10 34/35 | Year 11 35/36 | Year 12 36/37 | Year 13 37/38 | Year 14 38/39 | Year 15 39/40 | Total remaining 2025 - 2040 | Developer/ promoter | Summary Notes | new LP settlement hierarchy
Proposed H1 allocations without Planning Permission
H1Va | n/a | SJU001 | Land at Plainspot Farm, New Brinsley, Underwood | 1.56 | 42 | 42 | No permission | [9 empty] | 7 | 35 | [6 empty] | 42 | None currently known | Greenfield site on the edge of Brinsley Named Settlement. Consistent with Settlement Hierarchy. SHELAA site SJU001, deemed developable. | NS - Underwood
H1Vb | V/2023/0416 - Pending | SJU003 | Land off Westdale Road, Jacksdale | 2.1 | 64 | 64 | Pending decision | 0 | 0 | [5 empty] | 29 | 35 | [8 empty] | 64 | Keepmoat Homes | Existing site allocation within Named Settlement boundary of Jacksdale. Keepmoat - Full application pending V/2023/0416 for 64 dwellings. Site yield increased from 49 to reflect pending application. A draft section 106 agreement is currently being drawn up. | NS - Jacksdale
H1Vc | V/2022/0653 - pending | SJU014 | Land adj. Bull & Butcher PH, Selston | 6.6 | 149 | 149 | Pending decision | [6 empty] | 35 | 35 | 35 | 35 | 9 | [6 empty] | 149 | Central & Country | Application for 149 dwellings nearing determination Oct 2025. Recommended for approval at plannning committee 12th December 2025. | NS - Selston
H1Ve | V/2022/0800 - pending | SJU020 | Land off Park Lane/ South West M1, Selston | 9.39 | 137 | 137 | Pending decision |  |  |  |  | 32 | 35 | 35 | 35 | [9 empty] | 137 | Peveril Homes | Peveril Homes Full application V/2022/0800 pending for 137 dwellings Dwelling yield reduced from 169 to reflect advanced stage application. | NS - Selston
H1Vg | n/a | SJU031 + SJU043 | Land North of Larch Close, Underwood | 3.02 | 52 | 52 | No permission | [10 empty] | 17 | 35 | [5 empty] | 52 | None currently known | Gross developable area reduced to account for heavy tree cover and 20m highway corridor. | NS - Underwood
H1Vh | V/2025/0513 - pending (part of site) | SJU032 | Rear of 64-82 Church Lane, Underwood | 0.62 | 10 | 10 | Pending decision (part of site only) | 0 | 0 | [5 empty] | 5 | 5 | [8 empty] | 10 | Self Build/ Bi Design Architects | Greenfield site within Named Settlement boundary. Outline application pending on northern part of site for 5 dwellings (V/2025/0513) at October 2025. | NS - Underwood
H1Vi | n/a | SJU035 | Land off Westdale Road/ Rutland Road, Jacksdale | 0.5 | 22 | 22 | No permission | 0 | 0 | [7 empty] | 22 | [7 empty] | 22 | None currently known | Existing site allocation within Named Settlement boundary of Jacksdale. No current pipeline project. | NS - Jacksdale
| Total 'Rurals' sites without planning permission |  |  |  |  | 476 |  | 0 | 0 | 0 | 0 | 32 | 35 | 70 | 104 | 75 | 64 | 61 | 35 | 0 | 0 | 0 | 0 | 0 | 476
| Proposed H1 alllocations with Full/Reserved Matters/Detailed Planning Permission | [26 empty] | MUA
H1Vj | V/2022/0066 | SJU008 (part) | Land off Main Road, Jacksdale | 4.19 | 81 | 81 | Full/RM permission | 0 | 0 | 11 | 35 | 35 | [12 empty] | 81 | Peveril Homes | Peveril Homes - likely to come forward post completion of Millers Way, Kirkby (completed April 2025). S106 signed 10th April 2024. Street naming and numbering complete. Several conditions discharged in full 4/25. Development being marketed as Oak Tree Gardens on developer website as of October 2025. Commenecd on site as at November 2025. | NS - Jacksdale
| Total 'Rurals' Large Sites with Detailed Permission |  |  |  |  | 81 |  | 0 | 0 | 11 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81